## Tasks - Q4 - Internal IT - May
WBS | Task Name | Project Name | ProjectManager | Charge Code | Customer | Project Status | Planned Start Date | Planned Finish Date | Planned Duration | Planned Hours | Planned Cost | Planned Resource Cost | Percent Complete | Person | Linked From | Linked To | Actual Start Date | Actual Finish Date | Actual Duration | Actual Hours | Actual Cost | Actual Resource Cost | Remaining Hours | Milestone | Complete | Priority | Wbs | Locked | Baseline Duration | Baseline Hours | Baseline Start Date | Baseline Finish Date | Baseline Cost | Notes | Summary | Dependency (From) | Dependency (To) | Tags | Board | To Do list
1 | 1. Analysis | Q4 - Internal IT | Stephanie Ray | 111 | Internal | Not Started | 2024-08-15 | 2024-09-12 | 20 days | 62 hours | 0 | 1500 | 52 | [7 empty] | 0 | 0 | 62 hours | False | False | Medium | 1 | False | [5 empty] | Do stuff here. | True |  |  |  | To Do
1.1 | On-Site Meetings | Q4 - Internal IT | Stephanie Ray | 111 | Internal | Not Started | 2024-08-15 | 2024-08-21 | 4 days | 18 hours | 0 | 0 | 100 | Wayne Lawless [77.78 %] |  | Stakeholder Requirement 2, Stakeholder Requirement 1, Customer Requirement 1 |  |  |  |  | 0 | 0 | 18 hours | True | True | Medium | 1.1 | False | [5 empty] | Everything you need to describe the task can be listed here | False |  |  | Meeting | Done
1.2 | Discussions with Stakeholders | Q4 - Internal IT | Stephanie Ray | 111 | Internal | Not Started | 2024-08-20 | 2024-08-23 | 3 days |  | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 hours | False | False | Medium | 1.2 | False | [6 empty] | True |  |  |  | To Do
1.2.1 | Stakeholder Requirement 1 | Q4 - Internal IT | Stephanie Ray | 111 | Internal | Not Started | 2024-08-20 | 2024-08-21 | 1 day |  | 0 | 0 | 100 |  | On-Site Meetings | [5 empty] | 0 |  | 0 hours | False | True | Medium | 1.2.1 | False | [6 empty] | False |  |  | Request | Done
1.2.2 | Stakeholder Requirement 2 | Q4 - Internal IT | Stephanie Ray | 111 | Internal | Not Started | 2024-08-20 | 2024-08-21 | 1 day |  | 0 | 0 | 100 |  | On-Site Meetings | [5 empty] | 0 |  | 0 hours | False | True | Medium | 1.2.2 | False | [6 empty] | False |  |  | Request | Done
1.2.3 | Customer Requirement 1 | Q4 - Internal IT | Stephanie Ray | 111 | Internal | Not Started | 2024-08-20 | 2024-08-21 | 1 day |  | 0 | 0 | 100 |  | On-Site Meetings | [5 empty] | 0 |  | 0 hours | False | True | Medium | 1.2.3 | False | [6 empty] | False |  |  | Request | Done
1.3 | Document Current Systems | Q4 - Internal IT | Stephanie Ray | 111 | Internal | Not Started | 2024-08-29 | 2024-09-10 | 8 days | 12 hours | 0 | 1500 | 25 | Lindsay Hendrix |  | Analysis Complete |  |  |  |  | 0 | 0 | 12 hours | False | False | Medium | 1.3 | False | [6 empty] | False |  |  |  | Doing
1.4 | Analysis Complete | Q4 - Internal IT | Stephanie Ray | 111 | Internal | Not Started | 2024-09-10 | 2024-09-12 | 2 days | 32 hours | 0 | 0 | 0 | Wayne Lawless [50.00 %] | Document Current Systems | Design Database, Develop System Modules |  |  |  |  | 0 | 0 | 32 hours | True | False | Medium | 1.4 | False | [6 empty] | False |  |  |  | To Do
2 | 2. Design | Q4 - Internal IT | Stephanie Ray | 111 | Internal | Not Started | 2024-09-12 | 2024-10-04 | 16 days | 50 hours | 0 | 0 | 0 | [7 empty] | 0 | 0 | 50 hours | False | False | Medium | 2 | False | [6 empty] | True |  |  |  | To Do
2.1 | Design Database | Q4 - Internal IT | Stephanie Ray | 111 | Internal | Not Started | 2024-09-12 | 2024-09-18 | 4 days | 6 hours | 0 | 0 | 0 | Andrew Spear | Analysis Complete | Software Design |  |  |  |  | 0 | 0 | 6 hours | False | False | Medium | 2.1 | False | [6 empty] | False |  |  |  | To Do
2.2 | Software Design | Q4 - Internal IT | Stephanie Ray | 111 | Internal | Not Started | 2024-09-18 | 2024-09-25 | 5 days | 12 hours | 0 | 0 | 0 | Andrew Spear | Design Database | Interface Design |  |  |  |  | 0 | 0 | 12 hours | False | False | Medium | 2.2 | False | [6 empty] | False |  |  |  | To Do
2.3 | Interface Design | Q4 - Internal IT | Stephanie Ray | 111 | Internal | Not Started | 2024-09-25 | 2024-09-27 | 2 days | 8 hours | 0 | 0 | 0 | Andrew Spear | Software Design | Create Design Specification |  |  |  |  | 0 | 0 | 8 hours | False | False | Medium | 2.3 | False | [6 empty] | False |  |  |  | To Do
2.4 | Create Design Specification | Q4 - Internal IT | Stephanie Ray | 111 | Internal | Not Started | 2024-09-27 | 2024-10-04 | 5 days | 8 hours | 0 | 0 | 0 | Andrew Spear | Interface Design | Design Complete |  |  |  |  | 0 | 0 | 8 hours | False | False | Medium | 2.4 | False | [6 empty] | False |  |  |  | To Do
2.5 | Design Complete | Q4 - Internal IT | Stephanie Ray | 111 | Internal | Not Started | 2024-10-03 | 2024-10-04 | 1 day | 16 hours | 0 | 0 | 0 | Wayne Lawless [50.00 %], Andrew Spear [50.00 %] | Create Design Specification | [5 empty] | 0 | 0 | 16 hours | True | False | Medium | 2.5 | False | [6 empty] | False |  |  |  | To Do
3 | 3. Development | Q4 - Internal IT | Stephanie Ray | 111 | Internal | Not Started | 2024-09-16 | 2024-10-17 | 23 days |  | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 hours | False | False | Medium | 3 | False | [6 empty] | True |  |  |  | To Do
3.1 | Deploy Development Environment | Q4 - Internal IT | Stephanie Ray | 111 | Internal | Not Started | 2024-09-16 | 2024-09-17 | 1 day |  | 0 | 0 | 0 | [7 empty] | 0 |  | 0 hours | False | False | Medium | 3.1 | False | [6 empty] | False |  |  | Ticket | To Do
3.2 | Develop System Modules | Q4 - Internal IT | Stephanie Ray | 111 | Internal | Not Started | 2024-09-16 | 2024-10-01 | 11 days |  | 0 | 0 | 0 |  | Analysis Complete | Integrate System Modules, Perform System Testing |  |  |  |  | 0 |  | 0 hours | False | False | Medium | 3.2 | False | [6 empty] | False |  |  |  | To Do
3.3 | Integrate System Modules | Q4 - Internal IT | Stephanie Ray | 111 | Internal | Not Started | 2024-10-01 | 2024-10-10 | 7 days |  | 0 | 0 | 0 |  | Develop System Modules | Perform Initial Testing |  |  |  |  | 0 |  | 0 hours | False | False | Medium | 3.3 | False | [6 empty] | False |  |  |  | To Do
3.4 | Perform Initial Testing | Q4 - Internal IT | Stephanie Ray | 111 | Internal | Not Started | 2024-10-10 | 2024-10-15 | 3 days |  | 0 | 0 | 0 |  | Integrate System Modules | Development Complete |  |  |  |  | 0 |  | 0 hours | False | False | Medium | 3.4 | False | [6 empty] | False |  |  |  | To Do
3.5 | Development Complete | Q4 - Internal IT | Stephanie Ray | 111 | Internal | Not Started | 2024-10-14 | 2024-10-16 | 1 day |  | 0 | 0 | 0 |  | Perform Initial Testing | [5 empty] | 0 |  | 0 hours | True | False | Medium | 3.5 | False | [6 empty] | False |  |  |  | To Do
4 | 4. Testing | Q4 - Internal IT | Stephanie Ray | 111 | Internal | Not Started | 2024-10-14 | 2024-11-12 | 21 days |  | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 hours | False | False | Medium | 4 | False | [6 empty] | True |  |  |  | To Do
4.1 | Deploy Test Environment | Q4 - Internal IT | Stephanie Ray | 111 | Internal | Not Started | 2024-10-14 | 2024-10-15 | 1 day |  | 0 | 0 | 0 | [7 empty] | 0 |  | 0 hours | False | False | Medium | 4.1 | False | [6 empty] | False |  |  | Ticket | To Do
4.2 | Perform System Testing | Q4 - Internal IT | Stephanie Ray | 111 | Internal | Not Started | 2024-10-14 | 2024-10-24 | 8 days |  | 0 | 0 | 0 |  | Develop System Modules | Document Issues Found |  |  |  |  | 0 |  | 0 hours | False | False | Medium | 4.2 | False | [6 empty] | False |  |  |  | To Do
4.3 | Document Issues Found | Q4 - Internal IT | Stephanie Ray | 111 | Internal | Not Started | 2024-10-24 | 2024-11-01 | 6 days |  | 0 | 0 | 0 |  | Perform System Testing | Correct Issues Found |  |  |  |  | 0 |  | 0 hours | False | False | Medium | 4.3 | False | [6 empty] | False |  |  |  | To Do
4.4 | Bug 1 | Q4 - Internal IT | Stephanie Ray | 111 | Internal | Not Started | 2024-10-14 | 2024-10-15 | 1 day |  | 0 | 0 | 0 | [7 empty] | 0 |  | 0 hours | False | False | Medium | 4.4 | False | [6 empty] | False |  |  | Bug | To Do
4.5 | Bug 2 | Q4 - Internal IT | Stephanie Ray | 111 | Internal | Not Started | 2024-10-14 | 2024-10-15 | 1 day |  | 0 | 0 | 0 | [7 empty] | 0 |  | 0 hours | False | False | Medium | 4.5 | False | [6 empty] | False |  |  | Bug | To Do
4.6 | Correct Issues Found | Q4 - Internal IT | Stephanie Ray | 111 | Internal | Not Started | 2024-11-01 | 2024-11-06 | 3 days |  | 0 | 0 | 0 |  | Document Issues Found | Testing Complete |  |  |  |  | 0 |  | 0 hours | False | False | Medium | 4.6 | False | [6 empty] | False |  |  |  | To Do
4.7 | Testing Complete | Q4 - Internal IT | Stephanie Ray | 111 | Internal | Not Started | 2024-11-05 | 2024-11-06 | 1 day |  | 0 | 0 | 0 |  | Correct Issues Found | On-Site Installation |  |  |  |  | 0 |  | 0 hours | True | False | Medium | 4.7 | False | [6 empty] | False |  |  |  | To Do
5 | 5. Implementation | Q4 - Internal IT | Stephanie Ray | 111 | Internal | Not Started | 2024-11-06 | 2024-11-28 | 16 days |  | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 hours | False | False | Medium | 5 | False | [6 empty] | True |  |  |  | To Do
5.1 | On-Site Installation | Q4 - Internal IT | Stephanie Ray | 111 | Internal | Not Started | 2024-11-06 | 2024-11-12 | 4 days |  | 0 | 0 | 0 |  | Testing Complete | Setup Database, Train Administrators |  |  |  |  | 0 |  | 0 hours | False | False | Medium | 5.1 | False | [6 empty] | False |  |  |  | To Do
5.2 | Setup Database | Q4 - Internal IT | Stephanie Ray | 111 | Internal | Not Started | 2024-11-12 | 2024-11-15 | 3 days |  | 0 | 0 | 0 |  | On-Site Installation | Import Live Data |  |  |  |  | 0 |  | 0 hours | False | False | Medium | 5.2 | False | [6 empty] | False |  |  |  | To Do
5.3 | Import Live Data | Q4 - Internal IT | Stephanie Ray | 111 | Internal | Not Started | 2024-11-15 | 2024-11-22 | 5 days |  | 0 | 0 | 0 |  | Setup Database | Integrate Desktop |  |  |  |  | 0 |  | 0 hours | False | False | Medium | 5.3 | False | [6 empty] | False |  |  |  | To Do
5.4 | Integrate Desktop | Q4 - Internal IT | Stephanie Ray | 111 | Internal | Not Started | 2024-11-22 | 2024-11-27 | 3 days |  | 0 | 0 | 0 |  | Import Live Data | Implementation Complete |  |  |  |  | 0 |  | 0 hours | False | False | Medium | 5.4 | False | [6 empty] | False |  |  |  | To Do
5.5 | Implementation Complete | Q4 - Internal IT | Stephanie Ray | 111 | Internal | Not Started | 2024-11-26 | 2024-11-27 | 1 day |  | 0 | 0 | 0 |  | Integrate Desktop | Training Complete |  |  |  |  | 0 |  | 0 hours | True | False | Medium | 5.5 | False | [6 empty] | False |  |  |  | To Do
6 | 6. Training | Q4 - Internal IT | Stephanie Ray | 111 | Internal | Not Started | 2024-11-12 | 2024-11-28 | 12 days |  | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 hours | False | False | Medium | 6 | False | [6 empty] | True |  |  |  | To Do
6.1 | Train Administrators | Q4 - Internal IT | Stephanie Ray | 111 | Internal | Not Started | 2024-11-12 | 2024-11-15 | 3 days |  | 0 | 0 | 0 |  | On-Site Installation | Train Users |  |  |  |  | 0 |  | 0 hours | False | False | Medium | 6.1 | False | [6 empty] | False |  |  |  | To Do
6.2 | Train Users | Q4 - Internal IT | Stephanie Ray | 111 | Internal | Not Started | 2024-11-15 | 2024-11-20 | 3 days |  | 0 | 0 | 0 |  | Train Administrators | Training Complete |  |  |  |  | 0 |  | 0 hours | False | False | Medium | 6.2 | False | [6 empty] | False |  |  |  | To Do
6.3 | Training Complete | Q4 - Internal IT | Stephanie Ray | 111 | Internal | Not Started | 2024-11-26 | 2024-11-27 | 1 day |  | 0 | 0 | 0 |  | Train Users, Implementation Complete | Technical Documentation |  |  |  |  | 0 |  | 0 hours | True | False | Medium | 6.3 | False | [6 empty] | False |  |  |  | To Do
7 | 7. Documentation | Q4 - Internal IT | Stephanie Ray | 111 | Internal | Not Started | 2024-11-27 | 2024-12-10 | 9 days | 64 hours | 0 | 5240 | 0 | [7 empty] | 0 | 0 | 64 hours | False | False | Medium | 7 | False | [6 empty] | True |  |  |  | To Do
7.1 | Technical Documentation | Q4 - Internal IT | Stephanie Ray | 111 | Internal | Not Started | 2024-11-27 | 2024-11-30 | 3 days | 24 hours | 0 | 2040 | 0 | Jennifer Jones (Sample) [50.00 %], Mike Smith (Sample) [50.00 %] | Training Complete | User Documentation |  |  |  |  | 0 | 0 | 24 hours | False | False | Medium | 7.1 | False | [6 empty] | False |  |  |  | To Do
7.2 | User Documentation | Q4 - Internal IT | Stephanie Ray | 111 | Internal | Not Started | 2024-12-02 | 2024-12-07 | 5 days | 40 hours | 0 | 3200 | 0 | Jennifer Jones (Sample) | Technical Documentation | Project Complete |  |  |  |  | 0 | 0 | 40 hours | False | False | Medium | 7.2 | False | [6 empty] | False |  |  |  | To Do
7.3 | Project Complete | Q4 - Internal IT | Stephanie Ray | 111 | Internal | Not Started | 2024-12-06 | 2024-12-07 | 1 day |  | 0 | 0 | 0 | Jennifer Jones (Sample) | User Documentation | [5 empty] | 0 | 0 | 0 hours | True | False | Medium | 7.3 | False | [6 empty] | False |  |  |  | To Do